## Sprint 1 (17Oct-31Oct)
S/N | Status | Updated on | Type | Module | Description | Priority (determined by PM) | Assigned To (Assign back to PM when complete) | Aloysius | Christopher | Friedemann | Jason | Shahid | Zhen yuan
1 | Completed | 2016-10-31 | New module | User Access | Log in / out page for nurse to log into the system. Following which, nurse will be able to use check-in and assisted registration function | Medium | Christopher |  | C
2 | New | 2016-10-31 | New module | Content Customisation (Registration Form) |  | Medium
3 | In Progress | 2016-10-31 | New module | Visitor Logging (Online self-registration) |  | High
4 | In Progress | 2016-10-31 | New module | Visitor Logging (Assisted Registration) |  | High | Aloysius | A
5 | In Progress | 2016-10-31 | New module | Visitor Logging (Temp Screening and particulars check) |  | High | Aloysius | A
6 | In Progress | 2016-10-31 | New module | Visitor Logging (Checkpoints check-in) |  | High | Shahid |  |  |  |  | S
7 | In Progress | 2016-10-31 | New module | Visitor Logging (Checkpoint setup) |  | High | Shahid |  |  |  |  | S
8 | New | 2016-11-01 | Sub-task | Visitor Logging (Assisted Registration) | To differentiate between visitor (for patient) or visitor (others) | High | Aloysius | A
9 | New | 2016-11-01 | Sub-task | Visitor Logging (Assisted Registration) | Form Field validations (personal particulars + validation against patient database + check for X number of current visitors) | High | Aloysius | A
10 | New | 2016-11-01 | Sub-task | Visitor Logging (Assisted Registration) | Update screening questions | High | Aloysius | A
11 | New | 2016-11-01 | Sub-task | Visitor Logging (Temp Screening and particulars check) | Temperature alert for temperature exceeding X degrees | High | Aloysius | A
12 | New | 2016-11-01 | Sub-task | Visitor Logging (Temp Screening and particulars check) | Form Field validations (personal particulars + validation against patient database + check for X number of current visitors) | High | Aloysius | A
13 | New | 2016-11-01 | Sub-task | Visitor Logging (Checkpoint setup) | Include validation of user who activate terminal | High | Shahid |  |  |  |  | S
14 | New | 2016-11-01 | Sub-task | Visitor Logging (Checkpoints check-in) | Automatically take inputs from scanner. Put cursor on field automatically. Write to database | High | Shahid |  |  |  |  | S
15 | New | 2016-11-01 | Sub-task | Visitor Logging (Checkpoints check-in) | Entrance/exit terminals Checkpoint terminals | High | Shahid |  |  |  |  | S

## Sprint 2 (31Oct-6Nov)
S/N | Status | Updated on | Type | Module | Description | Priority (determined by PM) | Assigned To (Assign back to PM when complete) | Aloysius | Christopher | Friedemann | Jason | Shahid | Zhen yuan
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## workings
Status |  | Type | Priority | Assigned To
New | New module, not developed | New module | Ultra urgent | Aloysius
Incomplete | (others) | New task | High | Christopher
In Progress | Start development | Sub-task | Medium | Friedemann
In review | Testing | Bug | Low | Jason
Completed | Completed |  |  | Shahid
Zhen Yuan