## Work Break Down Structure
ANG MO KIO-THYE HUA KWAN HOSPITAL IS480 PROJECT
1.1 | INITIATION |  | 1.2 | PLANNING |  |  | EXECUTION |  | 1.4 | CONTROL |  | 1.5 | CLOSEOUT
1.1.1 | Evaluation and Recommendations | Pend | 1.2.1 | Create Preliminary Scope Statement | Pend | 1.3.1 | IT Project Team Kick off Meeting | Pend | 1.4.1 | Project Management | Pend | 1.5.1 | Audit Procurement | Pend
It is evaluated that AMK-THK Hospital needs to improve the Visitor Log system to include an online Contact Tracing System as Part of Infection Control System |  |  | Project Scope Statement: (a) Scope Statement - TBA |  |  | Grizzly Badger and IT Project Team discuss plan and assign responsibilties and timeline for status update from Persons-in-charge |  |  | Definition: (a) Milstones and deadlines (b) Cost and Quality criteria defined (c) Others |  |  | Ethnic Committee to ensure Patient Confidentiality requirements are complied.
1.1.2 | Develop Project Charter | Pend | 1.2.2 | Determine Project Team | Pend | 1.3.2 | Verify & Validate Users requirements | Pend | 1.4.2 | Project Status Meeting | Pend | 1.5.2 | Document Lessons Learnt | Pend
TBA |  |  | IT Project Team (proposed only): (a) Mr Edy Chandra (b) Mr Damien Tong (c) Dr Jocelyn Koh (d) Sister Quah (e) Sarah Lim |  |  | User Feedback |  |  | Proposed Meeting Schedule: (a) Every Tuesday, 2 PM at AMK-THK Hospital |  |  | Compile a 'Lessons Learnt' report for future reference for issues encountered in this project.
1.1.3 | Deliverable: Submit Project Charter | Pend | 1.2.3 | Project Team Kick off Meeting | Pend | 1.3.3 | Design System | Started | 1.4.3 | Risk Management | Pend | 1.5.3 | Update files and records | Pend
TBA |  |  | Project Team meet to (a) plan for IT solution (b) Budget the investment cost and total cost of ownership (c) Scheduling of work to be done |  |  | Proposed: (a) 1 x Server located in Branch Chair Office (b) 2 x Laptops for Registration Counter (c) 6 x Petition Writing desks (d) 2 x Cover Letter writing Station (ask vendor for automation) |  |  | Review: (a) Cyber security (b) Business Continuity (BCP) & Disaster Recovery Plan (DRP) |  |  | file all project notes, quotes and correspondence and build a file
1.1.4 | Sponsor Review Project Charter | Pend | 1.2.4 | Development Project Plan | Started | 1.3.4 | Procure Hardware and Software | Pend | 1.4.4 | Update Project Management Plan | Pend | 1.5.4 | Gain Formal Acceptance | Pend
TBA |  |  | TBA |  |  | TBA |  |  | TBA |  |  | User Acceptance Test and approval
1.1.5 | Project Charter finalised and approved | Done | 1.2.5 | Submit Project Plan | Pend | 1.3.5 | Install Development System | Pend |  |  |  | 1.5.5 | Archive files and documents | Pend
|  |  | Project Manager submit Plan to Acting CEO for approval | [8 empty] | TBA
|  |  | 1.2.6 | Milestone: Project Plan Approved | Pend | 1.3.6 | Testing Phase | Pend
|  |  | TBA |  |  | TBA
[6 empty] | 1.3.7 | Install Live Visitor Log System | Pend
TBA
[6 empty] | 1.3.8 | User Training | Pend
TBA
[6 empty] | 1.3.9 | Go Live | Pend
TBA

## Gantt Chart
PROJECT GANTT CHART
[6 empty] | MONTH | SEPTEMBER |  |  |  | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER
ID | ACTIVITIES | PERSON IN CHARGE | START [DATE] | END [DATE] | SCHEDULE TYPE | WEEK | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52
A | Prepare Layout and Project Scope |  |  |  | Planned
Actual
B | Form Project Team and assign roles and responsibilities |  |  |  | Planned
Actual
C | Project Plan review and confirmation |  |  |  | Planned
Actual
D | Validate User Requirements and Confirm Designs |  |  |  | Planned
Actual
E | Risk management and BCP/DRP Assessment |  |  |  | Planned
Actual
F | Contract Management and Procurement Process |  |  |  | Planned
Actual
G | Budgeting and Scheduling |  |  |  | Planned
Actual
H | Program Development Phase |  |  |  | Planned
Actual
I | Install Hardware or Hosting |  |  |  | Planned
Actual
J | Install Software and configure systems |  |  |  | Planned
Actual
K | Data Migration/ Data Entry of Parameters and Addresss |  |  |  | Planned
Actual
L | Live Testing |  |  |  | Planned
Actual
M | User Training |  |  |  | Planned
L |  |  |  |  | Actual
Legend

## Work Status Report
MEETING AND DISCUSSION | PLANNING | DECISION MAKING & DESIGNING | CONTRACTING PARTNERS | BUILDING SYSTEMS/RESOURCES | REMARKS
HR Director, Damien Tong explore IS480 with Prof Ben Gan (28/8/2016)
HR Director, Damien Tong pitch project to SMU teams in SMU School of Information System (2/10/2016)
Damien Tong and Edy Chandra discussed with Representatives of Grizzly Badgers, Chris Teo to review potential projects in AMK-THKH (23/9/2016)
Prof Ben Gan accept Visitor Log as Grizzly Badger's IS480 Project (29/9/2016)
Project Manager, Edy Chandra calls for Meeting to discuss New Triage System with cross-functional team (30/9/2016)

## Directory
CONTACT | COMPANY/ROLE | EMAIL | NUMBER
Prof Ben Gan | Project Supervisor | benjamingan@smu.edu.sg | 68280267
Damien Tong | Project Sponsor | damien_tong@amkh.org.sg | 81262212
Edy Chandra | Project Manager | edy_chandra@amkh.org.sg | 98292967
Damien Tong | Project Assistant Manager | damien_tong@amkh.org.sg | 81262212
Dr Jocelyn Koh | Head of Infection Control | jocelyn_koh@amkh.org.sg | 96268005
Chris Teo | IS480 Project Lead | mj.teo.2014@sis.smu.edu.sg | 91061923
Friedermann Ang | IS480 Project Members | zk.ang.2014@sis.smu.edu.sg
Aloysius LAM | IS480 Project Members | aloysiuslam.2014@sis.smu.edu.sg
Abdul Shahid Bin Rahmat | IS480 Project Members | abdulsr.2014@sis.smu.edu.sg
Jason Wu | IS480 Project Members | jason.wu.2014@sis.smu.edu.sg
Yu Zheng Yuan | IS480 Project Members | zyyu.2014@sis.smu.edu.sg