## Sprint 1 (17Oct-31Oct)
S/N | Status | Updated on | Type | Module | Description | Priority (determined by PM) | Assigned To (Assign back to PM when complete)
1 | Completed | 2016-10-31 | New module | User Access | Log in / out page for nurse to log into the system. Following which, nurse will be able to use check-in and assisted registration function | Medium | Christopher
2 | New | 2016-10-31 | New module | Content Customisation (Registration Form) |  | Medium
3 | In Progress | 2016-10-31 | New module | Visitor Logging (Online self-registration) |  | High
4 | In Progress | 2016-10-31 | New module | Visitor Logging (Assisted Registration) |  | High | Aloysius
5 | In Progress | 2016-10-31 | New module | Visitor Logging (Temp Screening and particulars validation) |  | High | Aloysius
6 | In Progress | 2016-10-31 | New module | Visitor Logging (Checkpoints check-in) |  | High | Shahid
7 | In Progress | 2016-10-31 | New module | Visitor Logging (Checkpoint setup) |  | High | Shahid
8
9
10
11
12
13
14
15

## Sprint 2 (31Oct-6Nov)
S/N | Status | Updated on | Type | Module | Description | Priority (determined by PM) | Assigned To (Assign back to PM when complete)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## workings
Status |  | Type | Priority | Assigned To
New | New module, not developed | New module | Ultra urgent | Aloysius
Incomplete | (others) | New task | High | Christopher
In Progress | Start development | Sub-task | Medium | Friedemann
In review | Testing | Bug | Low | Jason
Completed | Completed |  |  | Shahid
Zhen Yuan